## Sheet1
Category | No | Test Item | Test Name | Description | Test Flow (sequence used) | Pass Condition | Priority | UVM 1.1d Status | Blocked By | Action Items Required | Implementation Priority | Estimated Effort (Hours)
INSTRUCTION CACHE | 2.1 | Sequential Fetch | TC-I-01 | Verify sequential instruction fetch on I-Cache. Execute 8 NOPs @ 0x8000_0000. All hits (same cache line). PC increments automatically: 0x8000_0000, 0x8000_0004, 0x8000_0008, ... No AXI AR requests. | instruction_sequencer task Pre-loaded bootrom: 8x NOP PC chase (no branch) | hit_count == 8 miss_count == 0 No AXI AR requests PLRU state unchanged (same tag) | High | COMPATIBLE run_phase only Already PASSING (Phase 1) | None | None | MEDIUM | 0
| 2.2 | Branch Fetch | TC-I-02 | Verify I-Cache behavior on non-sequential fetch after branch. Execute JAL x1, 0x100. First fetch @ 0x8000_0000 (JAL instruction, miss). Second fetch @ 0x8000_0100 (jump target, miss). Two separate 256-bit cache lines. | instruction_decoder calculates jump target JAL instruction decoding required Sequence: Fetch @ 0x8000_0000 -> Decode JAL -> Fetch @ 0x8000_0100 | miss_count == 2 ar_count == 2 AXI address sequence: 0x8000_0000 -> 0x8000_0100 No instruction corruption | Medium | ADAPTED Requires instruction_decoder.sv integration Decoder.get_imm_j() -> PC + imm calculation Phase 2 Pending (2d effort) | A1, A4 | A1: Instruction decoder; A4: OBI VIF | CRITICAL | 2-3
| 2.3 | PLRU Replacement | TC-I-03 | Verify I-Cache PLRU replacement on conflict. Access 5 addresses mapping to same set: 0x8000_0000, 0x8000_4000, 0x8000_8000, 0x8000_C000, 0x8001_0000. Each 16KB apart triggers eviction. PLRU selects oldest victim on 5th miss. | instruction_sequencer task Fixed address pattern: 5 loads to 5 different tags, same set Deterministic sequence | hit_count == 1 (4th hit re-hits one line) miss_count == 4 (only 5th access causes eviction) PLRU tree evicts correct LRU entry | High | COMPATIBLE Already PASSING (Phase 1) Direct fetch pattern | A7 | A7: Update cache config | HIGH | 1-2
DATA CACHE | 3.1 | Store-Load Forwarding | TC-D-01 | Verify D-Cache write-through + load forwarding. Store value 0x1234 to base address, then immediately LOAD same address. Write-through: store commits immediately, LOAD reads from cache (hit). Scoreboard verifies LOAD RDATA == STORE WDATA. | obi_driver sequences CPU: ADDI x1, x0, 0x1234 SW x1, 0(x2) LW x3, 0(x2) Decoded by instruction_decoder | sb_pass_count >= 1 sb_fail_count == 0 LOAD returns written value (0x1234) Write-through verified | Critical | ADAPTED Requires instruction_decoder for LW/SW generation Map decoded load/store -> OBI data request Phase 2 Pending (2d effort) | A1, A4, A2 | A1: Decoder; A4: VIF; A2: Driver | CRITICAL | 2-3
| 3.2 | Load Sequence | TC-D-02 | Verify D-Cache hit/miss path on sequential loads. Execute 3 sequential LW to different base addresses (x2, x4, x6). Offsets: 0, 8, 16 (all within 64-byte line). First LW causes miss, second and third LW hit same cache line. | obi_driver sequences CPU: LW x1, 0(x2) LW x3, 8(x4) LW x5, 16(x6) Decoded address calculation: base + offset | sb_pass_count == 3 ar_count == 1 (only first miss) Hit rate: 2/3 All load values verified correct | Critical | ADAPTED Requires instruction_decoder for address calculation: base + offset Phase 2 Pending (2d effort) | A1, A4, A2, A7 | A1: Decoder; A4: VIF; A2: Driver; A7: Cache config | CRITICAL | 2-3
| 3.3 | FENCE.I Coherency | TC-D-03 | Verify FENCE.I invalidates I-Cache after self-modifying code. Overwrite instruction @ 0x8000_0000 via STORE, issue FENCE.I (flushes I-Cache), fetch modified instruction. Proves FENCE.I working and cache coherency. | obi_driver + instruction_decoder CPU: SW x1, 0(x2) (self-modify @ 0x8000_0000) FENCE.I (flush I-Cache) JAL to 0x8000_0000 (refetch modified) Sequence: Store -> FENCE.I -> Fetch | fence_invalidate_count == 1 miss_after_fence == 1 (I-Cache miss after FENCE.I) Line was invalidated New instruction fetched from memory | High | ADAPTED Requires FENCE.I decoding in instruction_decoder Write-through STORE then refetch Phase 2 Pending (2d effort) | A1, A4, A2 | A1: Decoder; A4: VIF; A2: Driver | HIGH | 2-3
PREFETCHER DATA CACHE | 4.1 | Stride Detection | TC-PF-01 | Verify Domino prefetcher detects stride pattern. Execute 4 sequential LW with fixed stride +0x100: LW @ 0x8000_0000, 0x8000_0100, 0x8000_0200, 0x8000_0300. Prefetcher learns A->B->C pattern, predicts C->D on 4th access. Prefetch AR issued BEFORE CPU LW request. | instruction_decoder + prefetcher monitor CPU: LW x1, 0(x2) LW x3, 0x100(x2) LW x5, 0x200(x2) LW x7, 0x300(x2) Stride fixed at +0x100 | prefetch_hit_count >= 1 OR ar_prefetch_count > 0 Hit rate improves: 0% (no prefetch) -> 25% (prefetch 4th) AXI ARVALID spike shows prefetch activity MHT1 learning verified | Critical | ADAPTED Requires instruction_decoder for address calculation Requires prefetcher monitor (trace MHT1 state) Phase 2 Pending (2d effort) | A1, A4, A8 | A1: Decoder; A4: VIF; A8: Prefetcher monitor | CRITICAL | 2-3
| 4.2 | Prefetcher Effectiveness | TC-PF-02 | Verify performance improvement from prefetcher. Run TC-PF-01 stride pattern twice: once with prefetcher disabled (all misses, baseline), once enabled (early prefetch hits). Measure stall cycles. Expected: 40% performance improvement. | instruction_decoder + prefetcher monitor Toggle: prefetch_enable_i signal Measure: total_cycles without prefetch vs with prefetch Stride pattern: same as TC-PF-01 (LW @ +0x100 intervals) | Performance improvement exists (cycles_no_pf - cycles_with_pf) / cycles_no_pf >= 0.3 stall_ratio improves with prefetcher enabled Prefetch saves ~30% stall time | Medium | ADAPTED Comparative measurement test Reuses TC-PF-01 sequences Phase 2 Pending (1d effort) | A1, A4, A8, A9 | A1: Decoder; A4: VIF; A8: Monitor; A9: Perf measurement | HIGH | 1-2
| 4.3 | XOR Hash Collision | TC-PF-02-EXT | Verify Domino MHT2 XOR hash distinguishes patterns. Train Pattern 1: A->B->X and Pattern 2: C->B->Y (different second orders). Replay A->B sequence. MHT2 XOR(A,B) should predict X not Y. Extended test from TC-PF-02. | instruction_decoder + prefetcher monitor CPU: Two training patterns with different second orders Monitor: MHT2 state & prefetch ARs Replay A, B sequence to trigger prediction | No UVM_ERROR/FATAL XOR hash collision handling correct Prefetch AR for X (not Y) after A->B replay 2nd-order prediction verified | High | ADAPTED Requires fixed tag patterns Requires prefetcher state visibility (MHT2 trace) Phase 2 Pending (1d effort) - Optional extension | A1, A4, A8 | A1: Decoder; A4: VIF; A8: Prefetcher monitor | HIGH | 1-2
STRESS / INTEGRATION | 5.1 | CPU Pipeline Baseline | TC-INT-01 | Verify basic CPU pipeline operation. Execute 32 NOP instructions sequentially. Baseline test: no cache misses, no data hazards, no stalls. Pipeline free-running. Validates instruction fetch and commit paths. | instruction_sequencer task 32x NOP pattern Pre-loaded bootrom | Commit count == 32 No stalls No pipeline flushes PLRU unchanged (single cache line) | High | COMPATIBLE Already PASSING (Phase 1) Baseline integration test | None | None | MEDIUM | 0
| 5.2 | Full L1 Stack Integration | TC-INT-02 | Verify all L1 components working together under realistic workload. Combined I-Cache + D-Cache + Prefetcher exercised simultaneously. Synthetic program: initialization loop + data processing loop with stride pattern. Final integration checkpoint for Phase 2. | obi_driver full integration Real program mix: - Fetch instructions (I-Cache) - Load/store data (D-Cache) - Repetitive stride pattern (Prefetcher trigger) Synthetic workload program | No UVM_ERROR/FATAL Simulation completes stall_ratio <= 0.3 (stalls < 100 for 100-cycle program) Cache statistics: hit%, miss%, prefetch% Prefetcher reduces stalls ~30% | Critical | ADAPTED Phase 2 Pending (3d effort) Uses TC-D-01 + TC-D-02 + TC-D-03 + TC-PF-01 + TC-PF-02 sequences combined Final integration test (depends on all Phase 2 tests passing) | A1-A9 (all Phase 2) | All action items (Phase 2 completion) | CRITICAL | 3

## Action Items Roadmap
Action ID | Task | Phase | Duration | Priority | Blocks | Dependency | Status
A1 | Create instruction_decoder.sv | Phase 1 | 2-3h | CRITICAL | TC-I-02, TC-D-01/02/03, TC-PF-01 | None | Pending
A2 | Update hpdcache_driver.sv port names | Phase 2 | 2-3h | HIGH | All 11 tests (signal driving) | A4 | Pending
A3 | Update hpdcache_monitor.sv port names | Phase 2 | 1-2h | HIGH | All 11 tests (observation) | A4 | Pending
A4 | Create cv32e40p_obi_adapter_if.sv | Phase 1 | 1-2h | CRITICAL | All 11 tests (VIF foundation) | None | Pending
A5 | Modify hpdcache_env.sv for CV32E40P | Phase 2 | 2h | HIGH | Environment elaboration | A2, A3 | Pending
A6 | Delete ISA-specific files + pkg cleanup | Phase 2 | 0.5h | MEDIUM | Package integrity | A5 | Pending
A7 | Extract & update HPDcache configuration | Phase 1 | 1-2h | MEDIUM | TC-I-03, TC-D-02/03 | None | Pending
A8 | Create prefetcher_monitor.sv | Phase 3 | 1-2h | MEDIUM | TC-PF-01/02/02-EXT (verification) | A4, A5 | Pending
A9 | Add performance measurement infrastructure | Phase 3 | 1-2h | LOW | TC-PF-02 (verification) | A8 | Pending

## Risk Assessment
Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy | Contingency Plan
R1 | Instruction decoder may require more complex logic than estimated | Medium | High | Start with RISC-V base ISA (LW, SW, JAL, FENCE.I), extend if needed | 2 days additional effort
R2 | OBI adapter port names may differ from assessment | High | High | Verify port names in CV32E40P RTL before A2/A3 implementation | 1 hour for port name correction
R3 | Prefetcher MHT1/MHT2 state may not be accessible in RTL | Medium | Medium | Check CV32E40P prefetcher RTL for state signals before A8 | Use observable signals only (1 day)
R4 | Cache configuration parameters differ significantly | Low | Medium | Extract exact parameters from cv32e40p_icache.sv early | Update test address patterns (2 hours)
R5 | Performance measurement may not correlate to actual improvement | Low | Medium | Use cycle-accurate simulation, verify against waveforms | Use prefetch_hit_count ratio as alternative metric (1 day)

## Execution Timeline
Phase | Phase Name | Duration | Key Actions | Completion Criteria | Status
1 | Foundation | 4-7h | A1, A4, A7 | All tests compile without errors; VIF foundation ready | Pending
2 | UVM Framework | 5.5-7.5h | A2, A3, A5, A6 | TC-I-01 & TC-INT-01 passing; environment elaborates correctly | Pending
3 | Test Extension | 2-4h | A8, A9 | All 11 tests functional; prefetcher verification working | Pending
4 | Refinement | 2-3h | Coverage, Assertions | All tests passing with >95% coverage; no assertion violations | Pending

## Summary
TESTPLAN UPDATE SUMMARY
File: | testplan_CV32E40P.xlsx
Updated: | 2026-07-26
Total Test Cases: | 11
Currently Passing: | 3 (TC-I-01, TC-I-03, TC-INT-01)
Pending Phase 2: | 8
KEY METRICS
Total Effort Estimated: | 14-22 hours
Critical Actions: | 3 (A1, A4, A7)
High Priority Actions: | 4 (A2, A3, A5, A6)
Tests Blocked by A1: | 5 (instruction decoder)
Tests Blocked by A4: | 11 (VIF foundation)
PHASE BREAKDOWN
Phase 1 (Foundation): | 4-7 hours | A1, A4, A7 | Compilation & VIF ready
Phase 2 (UVM Framework): | 5.5-7.5 hours | A2, A3, A5, A6 | Baseline tests passing
Phase 3 (Test Extension): | 2-4 hours | A8, A9 | All tests functional
Phase 4 (Refinement): | 2-3 hours | Coverage, Assertions | High-quality deliverable